## Sheet1
Task | Duration | Work Package | Duration | Resources | 2020-09-01 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 2020-10-01 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Conceptual Design | 5 |  |  | Online resources | Conceptual Design | bar: 2 to 5
CAD Model | 5 |  |  | CAD software |  | 6: CAD Model
Procurement of basic components | 5 |  |  | Local sellers |  | 11: Procurement of basic components
Mechanical Assembly | 10 |  |  | Local sellers |  | 16: Mechanical Assembly
|  | Table | 2 | Local sellers |  | 16: Table
|  | Table Top | 2 | Local sellers |  | 18: Table Top
|  | Welding Table top and Table | 2 | Local sellers |  | 20: Welding Table top and Table
|  | Attaching Bolts and Screws | 2 | Local sellers |  | 22: Attaching Bolts and Screws
|  | Building gun mount | 2 | Local sellers |  | 24: Buidling gun mount
Electrical Assembly | 10 |  |  | Local sellers |  | 26: Electrical Assembly
|  | Sync motors | 2 | Local sellers |  | 26: Sync motors
|  | Setting up motor drivers | 2 | Local sellers |  | 28: Setting up motor drivers
|  | Building Electronics Board | 4 | Local sellers |  | 30: Building Electronics Board |  |  |  | Setting up power supply
|  | Setting up power supply | 2 | Local sellers | [35 empty] | Rotating Assembly
Rotating Assembly | 10 |  |  | Local sellers | [35 empty] | Rotating screws
|  | Rotating screws | 2 | Local sellers | [37 empty] | Rails
|  | Rails | 3 | Local sellers | [40 empty] | Pulleys
|  | Pulleys | 3 | Local sellers | [43 empty] | Belts
|  | Belts | 2 | Local sellers | [45 empty] | Control Box
Control Box | 5 |  |  | Local sellers | [45 empty] | Desktop PC Setup
|  | Desktop PC Setup | 3 | Local sellers | [48 empty] | Switches
|  | Switches | 1 | Local sellers | [49 empty] | Emergency stop system
|  | Emergency stop system | 1 | Local sellers | [50 empty] | Final Assmbly and Testing
Final Assembly Testing | 10 |  |  | Comparing with standards
Total Days | 60